## Slide 1
Software engineering (Undergraduate)
Course Name software engineering
CSC 3114
(Undergraduate)
Chapter 6 The Dynamic Systems Development Method (DSDM)
Md Raihan Mahmud
Lecturer, CS, AIUB
raihan.mahmud@aiub.edu

## Slide 2: dsdm
The Dynamic Systems Development Method (DSDM) is a public domain Rapid Application Development method which has been developed through capturing the experience of a large group of vendor and user organisations.
It is now considered to be the UK's de-facto standard for RAD.
The key to DSDM is to deliver what business needs when it needs.
  Achieved by using the various techniques in the framework and flexing requirements
  The aim is always to address the current and imminent needs of the business rather than to attack all the perceived possibilities
Slide-2
SB

## Slide 3: Traditional method vs. Dsdm
Slide-3
Average time to delivery
(in months)
4-6
Average project team size
5
11
77%
87%
Using traditional approaches
Using DSDM
Source: British Airways IM Department, Newcastle
% of completed projects
rated good to excellent
18-24
SB

## Slide 4: Dsdm process view
Slide-4
SB

## Slide 5: Dsdm process
Slide-5
Activity | Sub activity | Description
Study | Feasibility Study | Stage where the suitability of DSDM is assessed. Judging by the type of project, organizational and people issues, the decision is made, whether to use DSDM or not. Therefore it will generate a FEASIBILITY REPORT, a FEASIBILITY PROTOTYPE, and a GLOBAL OUTLINE PLAN which includes a DEVELOPMENT PLAN and a RISK LOG.
 | Business Study | Stage where the essential characteristics of business and technology are analyzed. Approach to organize workshops, where a sufficient number of the customer’s experts are gathered to be able to consider all relevant facts of the system, and to be able to agree on development priorities. In this stage, a PRIORITIZED REQUIREMENTS LIST, a BUSINESS AREA DEFINITION, a SYSTEM ARCHITECTURE DEFINITION, and an OUTLINE PROTOTYPING PLAN are developed.
SB

## Slide 6: Dsdm process
Slide-6
Activity | Sub activity | Description
Functional Model Iteration | Identify functional prototype | Determine the functionalities to be implemented in the prototype that results from this iteration. In this sub-stage, a FUNCTIONAL MODEL is developed according to the deliverables result of business study stage.
 | Agree schedule | Agree on how and when to develop these functionalities.
 | Create functional prototype | Develop the FUNCTIONAL PROTOTYPE, according to the agreed schedule and FUNCTIONAL MODEL.
 | Review functional prototype | Check correctness of the developed prototype. This can be done via testing by end-user and/or reviewing documentation. The deliverable is a FUNCTIONAL PROTOTYPING REVIEW DOCUMENT.
SB

## Slide 7: Dsdm process
Slide-7
Activity | Sub activity | Description
Design and Build Iteration | Identify design prototype | Identify functional and non-functional requirements that need to be in the tested system. And based on these identifications, an IMPLEMENTATION STRATEGY is involved. If there is a TEST RECORD from the previous iteration, then it will be also used to determine the IMPLEMENTATION STRATEGY.
 | Agree schedule | Agree on how and when to realize these requirements.
 | Create design prototype | Create a system (DESIGN PROTOTYPE) that can safely be handed to end-users for daily use, also for testing purposes.
 | Review design prototype | Check the correctness of the designed system. Again, testing and reviewing are the main techniques used. A USER DOCUMENTATION and a TEST RECORD will be developed.
SB

## Slide 8: Dsdm process
Slide-8
Activity | Sub activity | Description
Implementation | User approval and guidelines | End users approve the tested system (APPROVAL) for implementation and guidelines with respect to the implementation and use of the system are created.
 | Train users | Train future end user in the use of the system. TRAINED USER POPULATION is the deliverable of this sub-stage.
 | Implement | Implement the tested system at the location of the end users, called as DELIVERED SYSTEM.
 | Review business | Review the impact of the implemented system on the business, a central issue will be whether the system meets the goals set at the beginning of the project. Depending on this the project goes to the next stage, the post-project or loops back to one of the preceding stages for further development. This review is will be documented in a PROJECT REVIEW DOCUMENT.
SB

## Slide 9: Difference between Traditional development vs. dsdm
Slide-9
Time
Resources
Functionality
Functionality
Time
Resources
Vary
Fixed
Traditional
DSDM
Traditional Method
Functional/requirements are fixed
Time & resources can vary
DSDM/Agile Methods
Functional/requirement varies
Time & resources are fixed
SB

## Slide 10: Techniques to consider in dsdm
Flexibility [80:20 Rule]
Timeboxing
MoSCoW Rules
Prototyping
Slide-10
SB

## Slide 11: Dsdm Techniques: flexibility
A fundamental assumption of DSDM is that nothing is built perfectly first time.
80:20 Rule: The 80/20 rule says that you can get 80% of the value from a project by focusing on the 20% of needs that are the most important.
DSDM assumes that all previous steps can be revisited as part of its iterative approach.
Therefore, the current step need be completed only enough to move to the next step, since it can be finished in a later iteration.
Slide-11
SB

## Slide 12: Dsdm Techniques: timeboxing
Without effective timeboxing, prototyping teams can lose their focus and run out of control.
Timeboxing works by concentrating on when a business objective will be met as opposed to the tasks which contribute to its delivery.
Timeboxing Basics
  Time between start and end of an activity
  DSDM uses nested timeboxes, giving a series of fixed deadlines
  Ideally 2 - 4 weeks in length
  Objective is to have easiest 80% produced in each timebox
  Remaining 20% potentially carried forward subsequent timeboxes
  Focus on the essentials
  Helps in estimating and providing resources
Slide-12
SB

## Slide 13: Dsdm Techniques: Moscow rules
MoSCoW rules formalised in DSDM version 3
Must have – fundamental to project success
Should have – important but project does not rely on
Could have – left out without impacting on project
Want to have but Won't have this time for those valuable requirements that can wait till later development takes place; in other words, the Waiting List.
Slide-13
SB
Category | Meaning | Example
Must-have | Essential requirements that are critical for system success. | User login functionality; data encryption; payment processing.
Should-have | Important features, but not vital for initial delivery. | Password reset option; mobile responsiveness; role-based access.
Could-have | Nice-to-have enhancements that have little impact if left out. | Dark mode; advanced analytics dashboard; chatbot.
Won’t-have (this time) | Least priority, out of scope for now, but may be considered in future. | Third-party integrations; multilingual support; gamification.

## Slide 14: Dsdm Techniques: prototyping
Prototypes are necessary in DSDM because
Facilitated workshops define the high-level requirements and strategy
Prototypes provide the mechanism through which users can ensure that the detail of the requirements is correct
Demonstration of a prototype broadens the users awareness of the possibilities and assists them in giving feedback to the developers
Speeds up the development process and increases confidence that the right solution will be delivered
Slide-14
SB

## Slide 15: references
R.S. Pressman & Associates, Inc. (2010). Software Engineering: A Practitioner’s Approach.
Kelly, J. C., Sherif, J. S., & Hops, J. (1992). An analysis of defect densities found during software inspections. Journal of Systems and Software, 17(2), 111-117.
Bhandari, I., Halliday, M. J., Chaar, J., Chillarege, R., Jones, K., Atkinson, J. S., & Yonezawa, M. (1994). In-process improvement through defect data interpretation. IBM Systems Journal, 33(1), 182-214.
Slide - 15
SB